## Release dates
Combined Release Schedule (Legacy & BUX)
Release | PROD Deployment
M107 | 2022-05-19
R133 | 2022-05-31
M108 | 2022-06-02
M109 | 2022-06-16
M110 | 2022-06-30
R134 | 2022-07-05
M111 | 2022-07-14
M112 | 2022-07-28
R135 | 2022-08-09
M113 | 2022-08-11
M114 | 2022-08-25
M115 | 2022-09-08
R136 | 2022-09-13
M116 | 2022-09-22
M117 | 2022-10-06
M118 | 2022-10-20
R137 | 2022-10-25
M119 | 2022-11-03
M120 | 2022-11-17
R138 | 2022-11-29
M121 | 2022-12-01
M122 | 2022-12-15
R139 | 2023-01-03
M123 | 2023-01-05

## Parameter definitions
Prioritization Parameters
Parameter | Description | Value(s) | Value Definitions
Due date | Date due for final or timeline phase delivery | Date | Calendar date
Critical defect | Remediation of critical production defect with significant customer impact | Yes | Yes = Functionality is broken with no alternative path
|  | No | No = Defect is broken but user has other options
Regulatory/Compliance urgency | Required by compliance mandate or regulatory directive | Critical | Critical = Immediate risk to shutdown of bank operations
|  | High | High = Elevated risk of negative regulatory action or fines
|  | Medium | Medium = UDAAP and regulatory concerns
|  | Low | Low = Preemptive compliance findings or concerns
Partner priority | Work is important to retail or BaaS partner | High | High = Contractual obligations or partner required upgrades
|  | Medium | Medium = Feature optimization or enhancement that increases product value proposition
|  | Low | Low = Minor updates
Product value | Non-revenue driven work such as feature optimization, contractual obligations or vendor required upgrades | High | High = Contractual obligations or required vendor upgrades
|  | Medium | Medium = Feature optimization or enhancement that increases product value proposition
|  | Low | Low = Minor updates
Marketing urgency | Work requested by marketing team | High | High = Work is part of scheduled campaign with timeline
|  | Medium | Medium = Non-timeline based work
|  | Low | Low = Content enhancement
InfoSec/Fraud/Risk urgency | Work required for security, fraud or risk enhancements | Critical | Critical = Current release
|  | High | High = Next release
|  | Medium | Medium = Within next 3 releases
|  | Low | Low = Within next 6 releases
Engineering urgency | Work required for tech debt or systems upgrades | High | High = Required upgrades
|  | Medium | Medium = Project/process/tools improvements
|  | Low | Low = Software upgrades and re-factoring/test case improvements
Revenue | Work requested for potential revenue | Projected revenue amount | Projected revenue contribution for calendar year in dollars (rounded to nearest $1k)
Defects | Non-critical defects | High | High = Loss of functionality impacting significant number of users
|  | Medium | Medium = Loss of functionality impacting low volume of users
|  | Low | Low = Inconveniences user but does not impact their ability to use functionality

## Red_TestData
Entry/Last Updated Date | Product Manager | Item | Jira Ticket | M109 6/16/22 | Critical Defect | Regulatory/Compliance Urgency | Partner Priority | Product Value | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency | Defects | Is this a Hard Date | Last Date of Prioritzation | Deferred | Override
June 13,2022 | Sharry Xu | Develop Jira tool | https://jira.com/browse/proj-001 | M109 | No | N/A | High | Low | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25 | Yes | Yes
June 13,2023 | Andy Wu | Review the design | https://jira.com/browse/proj-002 | M109 | Yes | High | N/A | High | N/A | N/A | Critical | N/A | N/A | Yes | 2022-05-25 | No | No
June 13,2023 | John Rease | Testing | https://jira.com/browse/proj-003 | M109 | Yes | Critical | High | High | N/A | N/A | Critical | N/A | N/A | Yes | 2022-05-25 | No | No
June 13,2023 | Harold Finch | PO Review | https://jira.com/browse/proj-004 | M110 | No | Low | High | High | N/A | N/A | Critical | N/A | N/A | Yes | 2022-05-25 | No | No
June 13,2023 | Tony Wei | Sign Off | https://jira.com/browse/proj-005 | M110 | Yes | High | N/A | Medium | N/A | N/A | Critical | N/A | N/A | Yes | 2022-05-25 | No | No

## Intake Form
Entry/Last Updated Date | Product Manager | Item | Jira Ticket | M109 6/16/22 | Critical Defect | Regulatory/Compliance Urgency | Partner Priority | Product Value | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency | Defects | Is this a Hard Date | Last Date of Prioritzation | Deferred | Override
May 20,2020 | Michelle Stone | Add logos for new eCash retailers in GO2 app | BMAPP-20293 from Epic https://pd.nextestate.com/browse/BMAPP-20336 | M109 6/16/22 | No | N/A | High | Low | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
2022-05-19 | Mark Sun | SCC closure/chargeoff: Refund to DDA | https://pd.nextestate.com/browse/GBOS-60614 | M109 6/16/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | Yes | 2022-05-25
2022-05-19 | Mark Sun | SCC payments: block fraud ACh accounts | https://pd.nextestate.com/browse/GSS-30861 there will be following impementation tickets | M110 6/30/22 | No | N/A | N/A | Medium | N/A |  | Medium | N/A | N/A | No | 2022-05-25
2022-05-19 | Mark Sun | SCC fees- Refund ATM Fees | https://pd.nextestate.com/browse/GBOS-58891 | M109 6/16/22 | Yes | High | N/A | High | N/A |  | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Mark Sun | Ability to Close SCC accounts that are not in NORMAL status | https://pd.nextestate.com/browse/GBOS-59197 | M110 6/30/22 | Yes | High | N/A | Medium | N/A |  | Medium | N/A | N/A | No | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] [QA only] FAQ Update | https://pd.nextestate.com/browse/BUX-36450 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] Opt-Out Flow | https://pd.nextestate.com/browse/BUX-36409 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Pooja Sharma | FIS Trancode Correction for Security Deposit payoff | https://pd.nextestate.com/browse/GBOS-62046 | M110 6/30/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] Overdrawn - Coverage fully utilized | https://pd.nextestate.com/browse/BUX-36404 | M109 6/16/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Android] [GO2bank] [ODP 2.0] FAQ Update | https://pd.nextestate.com/browse/BMAPP-21637 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Android] [GO2bank] [ODP 2.0] Opt Out Flow | https://pd.nextestate.com/browse/BMAPP-21632 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Android] [GO2bank] [ODP 2.0] Opt-In Flow | https://pd.nextestate.com/browse/BMAPP-21612 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [iOS] [GO2bank] [ODP 2.0] Opt Out Flow | https://pd.nextestate.com/browse/BMAPP-21529 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [iOS] [GO2bank] [ODP 2.0] Opt-In Flow | https://pd.nextestate.com/browse/BMAPP-21502 | M110 6/30/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
2022-05-20 | Sankeerth Bommi | [Automate] GO2bank ODP Fee Reversal | https://pd.nextestate.com/browse/GBOS-61531 | M111 7/14/22 | Yes | Critical | N/A | Medium | N/A |  | Low | N/A | Medium | No
2022-05-20 | Sankeerth Bommi | ODP 2.0 : OD Tier Downgrade at BCD : Look-Back interval and Count logic change | https://pd.nextestate.com/browse/GBOS-59170 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | ODP 2.0 : Raise cutoff for $200 ODP Tier from $400 to $1,000 | https://pd.nextestate.com/browse/GBOS-59465 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | ODP 2.0 : Logic change to remove continued Basic Tier eligibility after Direct Deposits stop | https://pd.nextestate.com/browse/GBOS-59373 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | ODP 2.0 : [Legacy] Logic change to remove continued Basic Tier eligibility after Direct Deposits stop | https://pd.nextestate.com/browse/COFO-44486 | R135 8/9/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | ODP 2.0 : [Legacy] Raise cutoff for $200 ODP Tier from $400 to $1,000 | https://pd.nextestate.com/browse/COFO-44474 | R135 8/9/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | [iOS/Android][GO2bank] [ODP 2.0] Go-Live | https://pd.nextestate.com/browse/BMAPP-21834 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] Go-Live (Desktop browser) | https://pd.nextestate.com/browse/BUX-37261 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] Go-Live (Mobile browser) | https://pd.nextestate.com/browse/BUX-37262 | M112 7/28/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Sankeerth Bommi | [Automate] GreenDot + Walmart ODP Fee Reversal | https://pd.nextestate.com/browse/COFO-45651 | R134 7/5/22 | Yes | Critical | N/A | Medium | N/A |  | Low | N/A | Medium | No | 2022-05-25
2022-05-20 | Sankeerth Bommi | [SCC] Send SCC closed update to FIS when we initiate the closure procedures | https://pd.nextestate.com/browse/GBOS-61523 | M113 8/11/22 | Yes | Critical | N/A | High | N/A |  | Low | N/A | Medium | Yes
2022-05-20 | Sankeerth Bommi | PPU Fee Takes account negative : No Grace Period Assigned and OD Fee Charged | https://pd.nextestate.com/browse/COFO-46490 | R136 9/13/22 | Yes | Critical | N/A | High | N/A |  | Low | N/A | High | Yes
2022-05-20 | Mirko | Enable CBR for QB | TBD | M113 8/11/22 | No | N/A | Medium | High | N/A | TBD | N/A | N/A | N/A | No
2022-05-20 | Mirko | Enable flexibility for CBR to be paid out for only signature or pin transactions, in addition to all spend transactions | TBD | M113 8/11/22 | No | N/A | Medium | High | N/A | TBD | N/A | N/A | N/A | No
2022-05-20 | Sankeerth Bommi | [Web] [GO2bank] [ODP 2.0] Overdrawn - Coverage not fully utilized | https://pd.nextestate.com/browse/BUX-36399 | M109 6/16/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
5/20/2022 Update hard date to yes on 6/3 | Mirko | New QB customers should no longer receive interest on main APY balance, only on savings - up to max balance of $100K. Existing should flip to same setup 30 days later | Research - https://pd.nextestate.com/browse/GBOS-61268 TBD for implementation | M109 6/16/22 | No | N/A | High | High | N/A | TBD | N/A | N/A | N/A | Yes | 2022-05-25
2022-05-20 | Mirko | Print check images in PDF | https://pd.nextestate.com/browse/GBOS-57774 | M109 6/16/22 | No | N/A | Low | Low | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Mirko | Enable instant out to debit card for QB / other BaaS partners | Research - https://pd.nextestate.com/browse/GBOS-60328 TBD for implementation | M109 6/16/22 | No | N/A | Medium | High | N/A | TBD | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Mirko | Enable wire out capability for QB | TBD | M113 8/11/22 | No | N/A | High | High | N/A | $7.5/wire | N/A | N/A | N/A | No
2022-05-20 | Mirko | Research on effort required to identify if receivable account (e.g. ABA/DDA) is an existing GD owned account and then facilitate transfer via P2P | Research - https://pd.nextestate.com/browse/GBOS-60805 | M109 6/16/22 | No | N/A | High | High | N/A | TBD | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Mirko | Remove incorrectly added fraud notes from CRM | Research - https://pd.nextestate.com/browse/GSS-25987 Implementation - TBD | M109 6/16/22 | No | N/A | Low | Low | N/A | N/A | N/A | N/A | Low | No | 2022-05-25
2022-05-20 | Mirko | Implement W9 backup withholdings | Research - https://pd.nextestate.com/browse/GBOS-56744 Wiki - https://wiki.nextestate.com/pages/viewpage.action?pageId=247466710 Implementation - TBD | M117 10/6/22 | No | Medium | Low | Low | N/A | N/A | N/A | N/A | N/A | No
2022-05-20 | Mirko | Allow expedited card shipments for BaaS partners through CRM | https://pd.nextestate.com/browse/GBOS-55886 | M113 8/11/22 | No | N/A | Low | Medium | N/A | N/A | N/A | N/A | N/A | No
2022-05-20 | Megan Ackling | Insert New Transtupe for PC nad PC Reversals | https://pd.nextestate.com/browse/COFO-46013 | R134 7/5/22 | No | N/A | N/A | High | N/A | N/A | High | N/A | N/A | Yes | 2022-05-25
2022-05-20 | Megan Ackling | Insert New TransclassAdjustmentDescriptionkKeys for CB and REPRE | https://pd.nextestate.com/browse/GBOS-61922 | R134 7/5/22 | No | N/A | N/A | High | N/A | N/A | High | N/A | N/A | Yes | 2022-05-25
2022-05-20 | Megan Ackling | Walgreens and CVS FeeSplit Setup for eCash Setup - GBOS | https://pd.nextestate.com/browse/FEAS-24667 | M111 7/14/22 | No | N/A | High | High | N/A | $227K Annual | N/A | N/A | N/A | No
2022-05-20 | Megan Ackling | Walgreens PayNearMe FeeSplit Setup | https://pd.nextestate.com/browse/FEAS-24544 | R134 7/5/22 | No | N/A | High | High | N/A | $227K Annual | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Megan Ackling | [QA Only][E2E] Walgreens PayNearMe RetailerKey Setup MOTX-79480 Enable PNM BINs with Walgreen - is a blocker for E2E testing. This story must be completed by Goldfinger before this story but after FEAS-24544 | https://pd.nextestate.com/browse/FEAS-24195 | R134 7/5/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | Yes
2022-05-20 | Megan Ackling | [QA Only]Test Fee Packages PPU20 & PPU15 - CoID 145 | https://pd.nextestate.com/browse/COFO-45223 | R134 7/5/22 | No | Low | N/A | N/A | N/A | N/A | Low | Low | N/A | No | 2022-05-25
2022-05-20 | Megan Ackling | [S1][SOS]Implement Speedway Check-Sum Barcode | https://pd.nextestate.com/browse/COFO-46015 | R134 7/5/22 | No | N/A | Medium | Medium | N/A |  | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Megan Ackling | Update Fee Packages to "FEPK15" and "FEPK14" | https://pd.nextestate.com/browse/FEAS-23961 | R134 7/5/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | High | Yes | 2022-05-25
2022-05-20 | Mirko | Allow CRM to issue refund checks for BaaS customers. Right now only possible for Go2Bank | Research - https://pd.nextestate.com/browse/GBOS-60750 Implementation - TBD | M109 6/16/22 | No | N/A | Low | Medium | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
2022-05-20 | Mirko | Add value name to merchant name field for reversed cash reloads | https://pd.nextestate.com/browse/GBOS-57232 | M109 6/16/22 | No | N/A | Low | Low | N/A | N/A | N/A | N/A | Low | No | 2022-05-25
May 20,2020 | Michelle Stone | Enable and test new retailers for eCash on GO2 | GSS-30774 and BUX-35776 from epic https://pd.nextestate.com/browse/BMAPP-20336 | M110 6/30/22 | No | N/A | High | Low | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Smitha Jonnala | [GBOS] Update Care Core Transfer history API to return the last 4 digit account number | GBOS-53063 | M109 6/16/22 | Yes | Medium | High | Medium | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2020 | Akhil Gupta | [Amazon Flex][CBR Rule]Update DB Rules To Have A Separate CBR Cap For A Set Of MCCs | https://pd.nextestate.com/browse/GBOS-58130 | M110 6/30/22 | No | N/A | Medium | Low | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 20,2020 | Akhil Gupta | [CBR] Execute SP - 'GetCashRewardEligibleInfo' in NEC to avoid the replication delay between NEC and NRT | https://pd.nextestate.com/browse/ARUS-25586 | R134 7/5/22 | Yes | High | Low | Low | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2020 | Akhil Gupta | Force users to upgrade app for the new EV Charging related front-end changes | https://pd.nextestate.com/browse/BUX-37196 | M110 6/30/22 | No | N/A | High | Medium | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Smitha Jonnala | [Go2bank][Android] Plaid Relink from V1 -> V2 using same account is showing an incorrect confirmation message | BMAPP-21936 | M110 6/30/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Smitha Jonnala | [Flex][Android] Plaid Relink from V1 -> V2 using same account is showing an incorrect confirmation message | BMAPP-21937 | M110 6/30/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Smitha Jonnala | [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | BMAPP-21860 | M109 6/16/22 | Yes | N/A | High | Medium | N/A | N/A | N/A | N/A | Medium | Yes | 2022-05-25
May 20,2022 | Smitha Jonnala | [GBOS] 4 Get ACH transfer list API to return the last 4 digit account number for all transactions | GBOS-61986 | M109 6/16/22 | Yes | N/A | High | Medium | N/A | N/A | N/A | N/A | Medium | Yes | 2022-05-25
May 20,2022 | Ziegler | BlackHawk eCash - Spike for DB and SP | https://pd.nextestate.com/browse/GSS-30055 | M109 6/16/22 | No | N/A | High | N/A | N/A | $50K in '22 | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Ziegler | New Swipe Program for Unit | https://pd.nextestate.com/browse/MOTX-78131 | R134 7/5/22 | No | N/A | High | N/A | N/A | $50K in '22 | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | StoreAPI for BankMobile Vibe | https://pd.nextestate.com/browse/MOTX-81150 | R134 7/5/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | PaymentUs - IP whitelist | https://pd.nextestate.com/browse/MOTX-81041 | R134 7/5/22 | No | N/A | High | N/A | N/A | $300K in '22 | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | PaymentVision - IP Whitelist | https://pd.nextestate.com/browse/MOTX-83014 | R134 7/5/22 | No | N/A | High | N/A | N/A | $30K in '22 | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | UniversalBarcode - DB config and New SP | https://pd.nextestate.com/browse/MOTX-79330 | R134 7/5/22 | No | N/A | N/A | Medium | N/A | $50K in '22 | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Ziegler | UniversalBarcode - New SP for barcode info | https://pd.nextestate.com/browse/MOTX-81089 | R134 7/5/22 | No | N/A | N/A | Medium | N/A | $50K in '22 | N/A | N/A | N/A | No | 2022-05-25
May 20,2022 | Ziegler | GFT - New API to retrieve the GDN BINs | https://pd.nextestate.com/browse/GDN-27816 | R134 7/5/22 | No | N/A | Medium | High | N/A | $60K in '22 | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | GFT - New API to GetProgramInfoByPan | https://pd.nextestate.com/browse/GDN-27817 | R134 7/5/22 | No | N/A | Medium | High | N/A | $60K in '22 | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | Acxiom Mock Service - Spike status and Simulator | https://pd.nextestate.com/browse/MOTX-82944 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | Medium | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | BlackHawk eCash - Spike for DB and SP at Retailer side | https://pd.nextestate.com/browse/GSS-30675 | M109 6/16/22 | No | N/A | High | N/A | N/A | $50K in '22 | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | ODP FAQ update | https://pd.nextestate.com/browse/GB-79515 | M109 6/16/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | Paypal API Migration - Conectivity Testing | https://pd.nextestate.com/browse/MOTX-77264 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | Paypal API Migration -Spike for Tech flow design | https://pd.nextestate.com/browse/MOTX-77263 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | N/A | N/A | Yes | 2022-05-25
May 20,2022 | Ziegler | [PNM][eCash]Enable PNM BINs with Walgreen | https://pd.nextestate.com/browse/MOTX-79480 | R134 7/5/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | Update LimitVerification to bypass phone/ssn limit check for internal test account | https://pd.nextestate.com/browse/ARUS-27913 | R134 7/5/22 | No | N/A | N/A | High | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | replace SP welcome email with SFMC | https://pd.nextestate.com/browse/ARUS-27357 | R134 7/5/22 | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-59633 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68663 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68668 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68702 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68708 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68713 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68455 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68460 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68819 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68824 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68829 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-68834 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | ODP WEB UX change | https://pd.nextestate.com/browse/WEB-69122 | R134 7/5/22 | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | [Gateway][Buyers Remorse] - Update refund card api to pass address | https://pd.nextestate.com/browse/WEB-68470 | R134 7/5/22 | No | Medium | N/A | Medium | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | Integrate api flag to switch between old and new ODP web flow | https://pd.nextestate.com/browse/BUX-36723 | R134 7/5/22 | No | Critical | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 21,2022 | Grace Huang | [Web][Buyers Remorse] Refund check (refund account) | https://pd.nextestate.com/browse/BUX-37348 | R134 7/5/22 | No | Medium | N/A | Medium | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 21,2022 | Grace Huang | [WEB][Moneypak] replease footer URL of 'where to buy' | [WEB-69173] [WEB][MoneyPak] - Replace link URL on footer - GDCJira (nextestate.com) | R134 7/5/22 | No | N/A | N/A | N/A | Medium | N/A | N/A | N/A | N/A | No | 2022-05-25
May 23,2023 | Sankeerth Bommi | [EUREKA OD ELIGIBILITY] Event trigger to notify OD engine when account status is changed because of IDV passed | https://pd.nextestate.com/browse/GBOS-54963 | M109 6/16/22 | Yes | High | N/A | High | Low | N/A | Low | Low | High | Yes | 2022-05-25
May 23,2023 | Megan Ackling | [QA Testing]ATM and AFT Limit Decrease for Regular Season - CoID 145 | https://pd.nextestate.com/browse/COFO-46541 | R134 7/5/22 | No | High | N/A | N/A | N/A | N/A | Medium | N/A | N/A | No | 2022-05-25
May 23,2023 | Megan Ackling | [QA Testing]ATM and AFT Limit Decrease for Regular Season - CoID 164 | https://pd.nextestate.com/browse/GBOS-62061 | M111 7/14/22 | No | High | N/A | N/A | N/A | N/A | Medium | N/A | N/A | No
May 24,2022 | Sylver Zhang | Turn on eStatement navigation panel in GD Mobile app | https://pd.nextestate.com/browse/GB-79581 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Sylver Zhang | Turn on eStatement navigation panel in GD Mobile app | https://pd.nextestate.com/browse/GB-79432 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Sylver Zhang | Align the eStatement navigation panel style between GD and Walmart | https://pd.nextestate.com/browse/GB-79582 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Sylver Zhang | Align the eStatement navigation panel style between GD and Walmart | https://pd.nextestate.com/browse/GB-79583 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Kinley Dong | Mobile and web [RushCard] [Meta rebrand] Change "MetaBank" to "Pathward" | https://pd.nextestate.com/browse/GB-79718 https://pd.nextestate.com/browse/COFO-46968 | R137 10/25/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes
May 24,2022 | Kinley Dong | [IOS][WMMC/GD][Medallia Integration]Integrate medallia SDK into WMMC & GD app | https://pd.nextestate.com/browse/GB-79301 | M112 7/28/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
May 24,2022 | Sylver Zhang | Introdcue flag control to return full transaction hisotry details including pending fees | https://pd.nextestate.com/browse/WEB-69230 | R134 7/5/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Sylver Zhang | Enhance CardAccount servcie to support full transaction hisotry return | https://pd.nextestate.com/browse/COFO-46715 | R134 7/5/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Grace Huang | [WEB][GD/WMT][Buyers' Remorse] - WEB to build a stand alone create user flow | [BUX-37771] [WEB][GD/WMT][Buyers' Remorse] - WEB to build a stand alone create user flow - GDCJira (nextestate.com) | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Grace Huang | [Gateway][Buyers Remorse] - map response code to indicate front-end errors that does not allow retry in refund account/refund pin | https://pd.nextestate.com/browse/BUX-37776 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Grace Huang | [WEB][GD/WMT][Buyers' Remorse] - Apply error message for negative scenario | https://pd.nextestate.com/browse/BUX-37781 | M109 6/16/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Grace Huang | ODP - [Gateway][ODP] - Return OD tier when in 'suspend' status | https://pd.nextestate.com/browse/WEB-69245 | R134 7/5/22 | No | High | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 24,2022 | Grace Huang | ODP - [ARUS][ODP] - Return OD tier when in suspense status | [ARUS-28001] [ARUS][ODP] - Return OD tier when in suspense status - GDCJira (nextestate.com) | R134 7/5/22 | No | High | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 2022-05-25
May 24,2022 | Rita Webb | Prove trust score can be turned off on Legacy system | https://pd.nextestate.com/browse/COFO-46599 | R134 7/5/22 | No | N/A | N/A | High | N/A |  | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Marc Moren | Update MMF Waiver Logic to include OCT credits | https://pd.nextestate.com/browse/PLA-25740 | R134 7/5/22 | No | High | N/A | N/A | N/A |  | N/A | N/A | High | No | 2022-05-25
May 24,2022 | Kinley Dong | [Android][WMMC/GD][Medallia Integration]Integrate medallia SDK into WMMC & GD app | https://pd.nextestate.com/browse/GB-79314 | M112 7/28/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
May 24,2022 | Danny Fong | Help Center for mobile app | https://pd.nextestate.com/browse/BUX-29250 | M114 8/25/22 | No | N/A | N/A | Low | Low | Low | N/A | N/A | N/A | No
May 24,2023 | Danny Fong | Deep link to RAF in mobile app | https://pd.nextestate.com/browse/BMAPP-21059 | M115 9/8/22 | No | N/A | N/A | N/A | Low | Low | N/A | N/A | N/A | No
May 24,2024 | Danny Fong | Prompt users to enable PNS after mobile app upgrade | https://pd.nextestate.com/browse/BMAPP-21865 | M116 9/22/22 | No | N/A | N/A | N/A | Low | Low | N/A | N/A | N/A | No
May 24,2022 | Sankeerth Bommi | ODP 2.0 : [Triggered Notification] NT105 - Overdraft - Tier Reinstated Incorrectly Triggered | https://pd.nextestate.com/browse/GBOS-61032 | M111 7/14/22 | Yes | High | N/A | High | Medium | N/A | Medium | N/A | High | Yes
May 24,2022 | Sankeerth Bommi | [Spike] ODP 2.0 : The "coverage remaining" should exclude any charged ODP Fees | https://pd.nextestate.com/browse/GBOS-62103 | M111 7/14/22 | Yes | High | N/A | High | High | N/A | Medium | N/A | High | Yes
May 24,2023 | Sankeerth Bommi | [Spike] ODP 2.0 : The "coverage remaining" should exclude any charged ODP Fees | https://pd.nextestate.com/browse/COFO-46853 | R134 7/5/22 | Yes | High | N/A | High | High | N/A | Medium | N/A | High | Yes | 2022-05-25
May 24,2023 | Sankeerth Bommi | [Data fix] Ability-to-pay check failed SCC account should be excluded when pick up no funding account within 100 days | https://pd.nextestate.com/browse/GBOS-60583 | M112 7/28/22 | Yes | Medium | N/A | Low | N/A | N/A | N/A | N/A | Medium | No
May 24,2023 | Sankeerth Bommi | SCC Statement external bank account Payment Option | https://pd.nextestate.com/browse/GBOS-61591 | M113 8/11/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | Medium | No
May 24,2023 | Sankeerth Bommi | [SCC] Route merchant reversals after account closure to DDA | https://pd.nextestate.com/browse/GBOS-61257 | M113 8/11/22 | No | Medium | N/A | N/A | N/A | N/A | N/A | N/A | Medium | No
May 24,2022 | Kerry li | Create EMV card for replacement | https://pd.nextestate.com/browse/GBOS-50188 | M110 6/30/22 | Yes | N/A | N/A | High | N/A | N/A | N/A | N/A | High | No | 2022-05-25
May 24,2022 | Kerry li | BaaS API Swagger Update 9 | https://pd.nextestate.com/browse/GBOS-58031 | M110 6/30/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Kerry li | BaaS API Swagger Update 10 | https://pd.nextestate.com/browse/GBOS-58032 | M109 6/16/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Kerry li | BaaS API Swagger Update 6 | https://pd.nextestate.com/browse/GBOS-58028 | M109 6/16/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Kerry li | BaaS API Swagger Update 7 | https://pd.nextestate.com/browse/GBOS-58029 | M109 6/16/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 24,2022 | Kerry li | [Stash][replaceCard]change product material type failed | https://pd.nextestate.com/browse/GBOS-55249 | M112 7/28/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
May 25,2022 | Marc Moren | Handle all ACH returns for originators | https://pd.nextestate.com/browse/COFO-46732 | M109 6/16/22 | No | N/A | Medium | N/A | N/A | 10000 | N/A | N/A | N/A | No | 2022-05-25
May 25,2022 | Charles Uyan | [SPIKE] Stop SP welcome email and send welcome email request to SFMC | https://pd.nextestate.com/browse/COFO-46670 | R134 7/5/22 | No | N/A | N/A | N/A | High | N/A | N/A | Medium | N/A | No | 2022-05-25
May 25,2022 | Charles Uyan | Decommission ActivationWelcomeEmail Stored Procedure | https://pd.nextestate.com/browse/WEB-67210 | R134 7/5/22 | No | N/A | N/A | N/A | High | N/A | N/A | Medium | N/A | No | 2022-05-25
May 25,2022 | Charles Uyan | Update ActivationWelcomeEmail Stored Procedure to Remove Prepaid | https://pd.nextestate.com/browse/COFO-46565 | R134 7/5/22 | No | Medium | N/A | N/A | High | N/A | N/A | N/A | Low | Yes | 2022-05-25
May 26,2022 | Ziegler | Modify paymentType for Visa BIN call to Mcsend | https://pd.nextestate.com/browse/MOTX-82578 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | N/A | N/A | Yes | 2022-05-25
2022-05-26 | Dennis Wiles | ATM Locator spike | https://pd.nextestate.com/browse/GBOS-61809 | M109 6/16/22 | No | High | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | 2022-05-25
May 26,2022 | Tyler Penn | [BaaS][OD EligibilityProcessor] Enhancement to add retry mechanism when call DB to get data | https://pd.nextestate.com/browse/GBOS-62054 | M111 7/14/22 | Yes | High | N/A | High | Medium | N/A | Medium | Medium | High | Yes | 2022-05-25
May 26,2022 | Megan Ackling | [QA Only]Test Update to Authorization Config for Fee Package FEPK13 (MTF 5/26/22, PROD 6/2/22) | https://pd.nextestate.com/browse/COFO-46956 | R134 7/5/22 | No | High | N/A | Medium | High | N/A | N/A | N/A | N/A | Yes
2022-05-26 | Marc Moren | Block ACH Credit with Individual Name of "Jetco Holdings" | https://pd.nextestate.com/browse/COFO-46971 | M109 6/16/22 | No | Low | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
2022-05-27 | Charles Uyan | [Publish Notification] Pass Available Balance attribute when triggering notifications | https://pd.nextestate.com/browse/GBOS-57038 | M110 6/30/22 | No | N/A | N/A | Low | Low | N/A | N/A | N/A | N/A | No
2022-05-27 | Smitha Jonnala | [Web] [GO2bank] Clean up ACH Plaid story - remove date and v1->v2 switch | https://pd.nextestate.com/browse/BUX-37962 | M110 6/30/22 | No | N/A | N/A | N/A | N/A | N/A | N/A | Medium | N/A | No
2022-05-31 | Charles Uyan | [Pinsearch]Create API for CRM to get pin infos | https://pd.nextestate.com/browse/FEAS-23633 | R134 7/5/22 | No | N/A | Medium | N/A | N/A | N/A | Medium | Medium | N/A | No
2022-05-31 | Robert Harada | New API to return ledger balance into AccountManagement Service. This story has to get done so Mustang Team can fix bug/defect on MOTX-73769 and MOTX-83056. | https://pd.nextestate.com/browse/COFO-45051 | R134 7/5/22 | Yes | N/A | N/A | High | N/A | N/A | N/A | N/A | High | Yes
2022-05-31 | Ziegler | Block transaction when retail info is missing for partner SOFI | https://pd.nextestate.com/browse/COFO-47299 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | N/A | N/A | Yes
2022-05-31 | Ziegler | IP whitelist for Swipe partner Viva First | https://pd.nextestate.com/browse/COFO-47190 | R134 7/5/22 | No | N/A | High | Medium | N/A |  | N/A | N/A | N/A | Yes
2022-06-01 | Sylver | Set up retailer level limit in Walgreens and BHN chain channels for eCash transaction involving GDN partner customers | https://pd.nextestate.com/browse/COFO-47247 | R134 7/5/22 | No | N/A | High | Medium | High |  | Medium | N/A | N/A | Yes
2022-05-31 | Mark Sun | [SCC][Android] Add event tracking to SCC acquisition flow | https://pd.nextestate.com/browse/BMAPP-22027 | M109 6/16/22 | No | N/A | N/A | High | N/A |  | N/A | N/A | Medium | No
2022-05-31 | Mark Sun | [SCC][iOS] Add event tracking to SCC acquisition flow | https://pd.nextestate.com/browse/BMAPP-22024 | M109 6/16/22 | No | N/A | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC payments: ACH payments reminder | https://pd.nextestate.com/browse/GBOS-62108 | M111 7/14/22 | Yes | Critical | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC payments: ACh return notifications | https://pd.nextestate.com/browse/GBOS-62135 | M111 7/14/22 | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | Medium | No
2022-05-31 | Mark Sun | SCC payments: ACH payment date | https://pd.nextestate.com/browse/BMAPP-21518 | M112 7/28/22 | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC payments: ACH payment date | https://pd.nextestate.com/browse/BMAPP-21517 | M112 7/28/22 | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC payments: ACH payment date | https://pd.nextestate.com/browse/BUX-38126 | M112 7/28/22 | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC statement: Cash advance description | https://pd.nextestate.com/browse/GBOS-59678 | M113 8/11/22 | No | Medium | N/A | Medium | N/A |  | N/A | N/A | Medium | No
2022-05-31 | Mark Sun | SCC Statement external bank account Payment Option | https://pd.nextestate.com/browse/GBOS-61591 | M112 7/28/22 | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | Medium | No
2022-05-31 | Mark Sun | [SCC] Add Payment Source to NT 186 | https://pd.nextestate.com/browse/GBOS-62109 | M113 8/11/22 | No | N/A | N/A | Medium | N/A |  | N/A | N/A | N/A | No
2022-06-01 | Mark Sun | [Spike] SCRA/MLA audit | https://pd.nextestate.com/browse/GBOS-57994 | M112 7/28/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | No
2022-06-01 | Sankeerth Bommi | [SCC] [Statement][LMS] Show the balance subject to the interest charged in the current cycle - Part2 | https://pd.nextestate.com/browse/GBOS-62194 | M112 7/28/22 | No | Medium | N/A | Medium | N/A |  | N/A | N/A | N/A | No
2022-06-01 | Tyler Penn | Spike - [BaaS][OD EligibilityProcessor] Enhancement to add retry mechanism when call DB to get data | https://pd.nextestate.com/browse/GBOS-62193 | M110 6/30/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | No
2022-06-01 | Smitha Jonnala | Splunk report- mismatch between records in splunk vs email report | https://pd.nextestate.com/browse/GBOS-61888 | M110 6/30/22 | No | N/A | Medium | Medium | N/A | N/A | N/A | N/A | Medium | No
2022-06-02 | Sankeerth Bommi | Fix data in FIS and issue refund for SCRA Customers | https://pd.nextestate.com/browse/GBOS-58655 | M113 8/11/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | No
2022-06-02 | Sankeerth Bommi | Large font statements for all NY based customers | https://pd.nextestate.com/browse/GBOS-58164 | M117 10/6/22 | No | Low | N/A | Medium | N/A |  | Low | N/A | N/A | No
2022-06-02 | Sankeerth Bommi | [Customer Notification][GO2bank SCC] OFAC - Hard Decline | https://pd.nextestate.com/browse/GBOS-39848 | M111 7/14/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | Yes
2022-06-02 | Sankeerth Bommi | [SCC] Trigger OFAC Hard Decline | https://pd.nextestate.com/browse/GBOS-39660 | M112 7/28/22 | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [Trigger Notification][GO2bank] NT295 - Overdraft - 10 ODP Fees within 2 Months | https://pd.nextestate.com/browse/GBOS-60784 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For No DD in last 45 days | https://pd.nextestate.com/browse/GBOS-62110 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For Suspicious Activity | https://pd.nextestate.com/browse/GBOS-62111 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For Negative Balance over 45 days | https://pd.nextestate.com/browse/GBOS-62112 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey99] Temp Paused For 10 Transaction Limit | https://pd.nextestate.com/browse/GBOS-62113 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey100] OD2/OD3 Overdraft Spend - Initial Transaction | https://pd.nextestate.com/browse/GBOS-62114 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey105] Tier Reinstated | https://pd.nextestate.com/browse/GBOS-62115 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey187] OD1 Overdraft Spend | https://pd.nextestate.com/browse/GBOS-62118 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (No Eligible Direct Deposit) | https://pd.nextestate.com/browse/GBOS-61909 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (Account Status) | https://pd.nextestate.com/browse/GBOS-61910 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (Negative Balance) | https://pd.nextestate.com/browse/GBOS-61911 | M113 8/11/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For Negative Balance over 45 days | https://pd.nextestate.com/browse/COFO-46961 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For Suspicious Activity | https://pd.nextestate.com/browse/COFO-46962 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR CN] Temp Paused For No DD in last 45 days | https://pd.nextestate.com/browse/COFO-46963 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey306] Temp Paused For 10 Transaction Limit | https://pd.nextestate.com/browse/COFO-46964 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey307] Tier Reinstated | https://pd.nextestate.com/browse/COFO-46965 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (No Eligible Direct Deposit) | https://pd.nextestate.com/browse/COFO-46760 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (Account Status) | https://pd.nextestate.com/browse/COFO-46761 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Tyler Penn | [Customer Notification] New Overdraft - Temporarily Paused (Negative Balance) | https://pd.nextestate.com/browse/COFO-46770 | R136 9/13/22 | No | High | N/A | High | N/A |  | Low | N/A | N/A | Yes
2022-06-02 | Megan Ackling | Research the Return mail vendor change. (Spike Story, Impacts Legacy and BaaS) | https://pd.nextestate.com/browse/GSS-31173 | M110 6/30/22 | No | High | Low | Low | N/A | N/A | N/A | N/A | N/A | Yes
2022-06-02 | Megan Ackling | Modify 'Credit Rating Change' to check for a Perso Card on the Acct I believe this story will need SOS. I left a comment to have Irene review. | https://pd.nextestate.com/browse/COFO-48580 | R135 8/9/22 | No | Low | Low | Medium | N/A |  | Low | N/A | N/A | No
2022-06-03 | Sankeerth Bommi | [Go2bank][BaaS][Overdraft] Suspension History | https://pd.nextestate.com/browse/CRM-51520 | R136 9/13/22 | No | Medium | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-06-03 | Sankeerth Bommi | [CareMT][BaaS][Overdraft] Highlight Transactions Related to Overdraft | https://pd.nextestate.com/browse/GBOS-61638 | M112 7/28/22 | No | Medium | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-06-03 | Sankeerth Bommi | [Go2bank][BaaS][Overdraft] Highlight Transactions Related to Overdraft | https://pd.nextestate.com/browse/CRM-49887 | R135 8/9/22 | No | Medium | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-06-03 | Greg Schimmel/Veronica Ramos | [Rush] [NegBal] Accept Negative Credits via PSBF File | https://pd.nextestate.com/browse/COFO-45774 | M110 6/30/22 | Yes | Medium | High | High | N/A |  | N/A | N/A | N/A | No | Need to provide Meta with a timeframe for completion.
2022-06-03 | Grace Huang | [WEB][ODP][GD/WMT] Enable opt out when account in Bad status or Negative Balance | https://pd.nextestate.com/browse/WEB-69369 | R134 7/5/22 | Yes | High | N/A | High | N/A | $1.5M | N/A | N/A | N/A | Yes
2022-06-03 | Mirko | QB APY Updates - Part 1 | https://pd.nextestate.com/browse/GBOS-62219 | M110 6/30/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | Yes
2022-06-03 | Mirko | QB APY Updates - Part 2 | https://pd.nextestate.com/browse/GBOS-62220 | M112 7/28/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | Yes
2022-06-03 | Mirko | Allow SMB BaaS partners to cancel pending ACH Pull transactions | https://pd.nextestate.com/browse/GBOS-62222 | M111 7/14/22 | No | N/A | Low | Low | N/A |  | N/A | N/A | N/A | No
2022-06-03 | Mirko | Allow SMB BaaS partners to update business name via name change API | https://pd.nextestate.com/browse/GBOS-60359 | M113 8/11/22 | No | N/A | Low | Low | N/A |  | N/A | N/A | N/A | No
2022-06-03 | Grace Huang | Pull off outdated tax season banner from GD.com | https://pd.nextestate.com/browse/WEB-65664 | R134 7/5/22 | No | Medium | N/A | Low | High |  | N/A | N/A | N/A | Yes | JIra is too slow, I put a place holder story there, I'll in the detail once Jira is back. This is a small effort item but have higher marketing urgency. thanks.
2022-06-03 | Grace Huang | [IOS][ODP][GD/WMT] - do not allow user to opt out when in suspense status | https://pd.nextestate.com/browse/GB-80005 | R135 8/9/22 | Yes | High | N/A | High | N/A | $1.5M | N/A | N/A | N/A | Yes
2022-06-03 | Grace Huang | [Android][ODP][GD/WMT] - do not allow user to opt out when in suspense status | https://pd.nextestate.com/browse/GB-80018 | R135 8/9/22 | Yes | High | N/A | High | N/A | $1.5M | N/A | N/A | N/A | Yes
2022-06-03 | Grace Huang | [WEB][ODP][GD/WMT] - Allow user in suspense status to land on OD intro page | https://pd.nextestate.com/browse/WEB-69374 | R135 8/9/22 | Yes | High | N/A | High | N/A | $1.5M | N/A | N/A | N/A | Yes
2022-06-06 | Ziegler | New eCash Program for PaymentUs | https://pd.nextestate.com/browse/COFO-46875 | R136 9/13/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | Yes
2022-06-06 | Ziegler | New eCash Program for PaymentVision | https://pd.nextestate.com/browse/COFO-46888 | R135 8/9/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | Yes
2022-06-06 | Ziegler | Send Store info to MCSend for GSS-POB | https://pd.nextestate.com/browse/GSS-30322 | M110 6/30/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Send PartnerProgram to GDN Partner for Varo | https://pd.nextestate.com/browse/COFO-47452 | R135 8/9/22 | No | N/A | Medium | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Return Customerfee in ReloadAPI for Legacy GDN Partner | https://pd.nextestate.com/browse/COFO-47460 | R135 8/9/22 | No | N/A | Medium | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Add logic for Check-Sum for Speedway - DB | https://pd.nextestate.com/browse/GSS-30854 | M111 7/14/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Add logic for Check-Sum for Speedway - Code | https://pd.nextestate.com/browse/GSS-30687 | M111 7/14/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Send Store info to MCRepower | https://pd.nextestate.com/browse/COFO-49158 | R134 7/5/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Grace Huang | [WEB][WMT][ODP] - FAQ updates | [WEB-68653] [WEB][WMT][ODP] - FAQ updates - GDCJira (nextestate.com) | R134 7/5/22 | No | Critical | N/A | High | High | N/A | N/A | N/A | N/A | Yes
2022-06-06 | Mark Sun | [SCC] [data fix] Charged off accounts didn't get closed | https://pd.nextestate.com/browse/GBOS-62233 | M110 6/30/22 | Yes | Critical | N/A | High | N/A |  | N/A | N/A | High | No
2022-06-06 | Mark Sun | [SCCBatchProcessorJob_Delinquincy] Add an ability to reprocess failed accounts | https://pd.nextestate.com/browse/GBOS-62234 | M110 6/30/22 | Yes | Critical | N/A | High | N/A |  | N/A | N/A | High | No
2022-06-06 | Sarath Krishnan | [GFT][MCsend]Create Adjusmentypes for Partner A2A and P2P | https://pd.nextestate.com/browse/GBOS-61750 | M111 7/14/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Sarath Krishnan | [GFT][Chime]Modify Link Card API Mandatory Fields based on Program code. | https://pd.nextestate.com/browse/GBOS-62236 | M111 7/14/22 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No
2022-06-06 | ?? (submitted by May Shoua Moua) | SoFi Requirement: Store Number Transformation - Pilot InComm (RCK = 475) | [COFO-47274] Store Number Transformation - Pilot InComm (RCK = 475) - GDCJira (nextestate.com) | M110 6/30/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | Yes
2022-06-07 | Charles Uyan | [Legacy] Pass Account Key when Notification Type Key 136 is Triggered | https://pd.nextestate.com/browse/COFO-49287 | R134 7/5/22 | No | N/A | N/A | Medium | Medium |  | N/A | N/A | N/A | Yes
2022-06-07 | Charles Uyan | Send Notification on CRV removal for PAYG product | https://pd.nextestate.com/browse/COFO-46571 | R134 7/5/22 | No | N/A | N/A | Medium | Medium |  | N/A | N/A | N/A | Yes
2022-06-07 | Smitha Jonnala | [WMMC] OAuth redirect is not working as expected | https://pd.nextestate.com/browse/GB-80048 | M111 7/14/22 | Yes | N/A | N/A | Medium | N/A | N/A | N/A | N/A | Medium | Yes
2022-06-08 | Ziegler | [GSS-POB]Add New BINs to existing Partner Revolut | https://pd.nextestate.com/browse/GSS-31228 | M110 6/30/22 | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-08 | Ziegler | [UberRider]Spike impacted for increase length of PartnerRequestID when Generate Barcode | https://pd.nextestate.com/browse/COFO-49305 | R134 7/5/22 | Yes | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No

## Data
Due Date | Critical Defect | Priority Urgency | Sprint / Release | Sprint End Date / PROD Deployment Date | Prioritization Grouping
M107 5/19/22 | Yes | Critical | R134 S1 | 2022-06-14 | R134 S1 + M109
R133 5/31/22 | No | High | M109 | 2022-06-16
M108 6/2/22 |  | Medium | R134 S2 | 2022-06-28 | R134 S2 + M110
M109 6/16/22 |  | Low | M110 | 2022-06-30
M110 6/30/22 |  | N/A | M111 | 2022-07-14 | M111 + R135 S1
R134 7/5/22 |  |  | R135 S1 | 2022-07-19
M111 7/14/22 |  |  | M112 | 2022-07-28 | M112 + R135 S2
M112 7/28/22 |  |  | R135 S2 | 2022-08-02
R135 8/9/22 |  |  | M113 | 2022-08-11 | M113 + R136 S1 + M114
M113 8/11/22 |  |  | R136 S1 | 2022-08-23
M114 8/25/22 |  |  | M114 | 2022-08-25
M115 9/8/22 |  |  | R136 S2 | 2022-09-06 | R136 S2 + M115
R136 9/13/22 |  |  | M115 | 2022-09-08
M116 9/22/22 |  |  | M116 | 2022-09-22 | M116 + R137 S1
M117 10/6/22 |  |  | R137 S1 | 2022-09-27
M118 10/20/22 |  |  | M117 | 2022-10-06 | M117 + R137 S2 + M118
R137 10/25/22 |  |  | R137 S2 | 2022-10-18
M119 11/3/22 |  |  | M118 | 2022-10-20
M120 11/17/22 |  |  | M119 | 2022-11-03 | M119 + R138 S1
R138 11/29/22 |  |  | R138 S1 | 2022-11-08
M121 12/1/22 |  |  | M120 | 2022-11-17 | M120 + R138 S2
M122 12/15/22 |  |  | R138 S2 | 2022-11-22
R139 1/3/23 |  |  | M121 | 2022-12-01 | M121 + R139 S1
M123 1/5/23 |  |  | R139 S1 | 2022-12-13
|  |  | M122 | 2022-12-15 | M122 + R139 S2
|  |  | R139 S2 | 2022-12-27

## Schedule
Sprint / Release | Sprint End Date / PROD Deployment Date
M109 | 2022-06-16
M110 | 2022-06-30
M111 | 2022-07-14
M112 | 2022-07-28
M113 | 2022-08-11
M114 | 2022-08-25
M115 | 2022-09-08
M116 | 2022-09-22
M117 | 2022-10-06
M118 | 2022-10-20
M119 | 2022-11-03
M120 | 2022-11-17
M121 | 2022-12-01
M122 | 2022-12-15
R134 S1 | 2022-06-14
R134 S2 | 2022-06-28
R135 S1 | 2022-07-19
R135 S2 | 2022-08-02
R136 S1 | 2022-08-23
R136 S2 | 2022-09-06
R137 S1 | 2022-09-27
R137 S2 | 2022-10-18
R138 S1 | 2022-11-08
R138 S2 | 2022-11-22
R139 S1 | 2022-12-13
R139 S2 | 2022-12-27

## Sample Intake form
Item | Due Date | Critical Defect | Regulatory/Compliance Urgency | Product Value | Partner Priority | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency
Project Name | M108 | No | N/A | High | N/A | N/A | 125000 | N/A | N/A
Defect Name | M110 | No | N/A | Medium | N/A | High | N/A | N/A | N/A
Partner Project | M110 | No | N/A | High | N/A | N/A | N/A | N/A | N/A
Retail Project | R134 | No | N/A | High | N/A | Medium | N/A | N/A | N/A
Retail Defect | M113 | No | N/A | Medium | N/A | High | N/A | N/A | N/A