## Sheet1
Entry/Last Updated Date | Product Manager | Item | Jira Ticket | Milestone/Release Due Date | Critical Defect | Regulatory/Compliance Urgency | Partner Priority | Product Value | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency | Defects | Is this a Hard Date | Last Date of Prioritzation | Deferred | Override
2022-06-14 | Mark Sun | [QA][Go-Live] Refund ATM Fees over 25% of credit limit in first year | https://pd.nextestate.com/browse/GBOS-62337 | M111 | Yes | Critical | High | High | N/A |  | Medium | N/A | High | Yes | 2022-06-23
2022-05-20 | Tyler Penn | [Automate] GO2bank ODP Fee Reversal | https://pd.nextestate.com/browse/GBOS-61531 | M111 | Yes | Critical | N/A | Medium | N/A |  | Low | N/A | Medium | No | 2022-06-23
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey105] Tier Reinstated | https://pd.nextestate.com/browse/GBOS-62115 | M111 | Yes | High | N/A | High | N/A |  | Low | N/A | High | Yes | 2022-06-23
2022-06-15 | Mark Sun | [SCC] Block non-SSN DDA applying for an SCC | https://pd.nextestate.com/browse/GBOS-62345 | M111 | No | Critical | Low | Medium | N/A |  | High | High | High | No | 2022-06-23
2022-06-22 | Tyler Penn | [Gateway] [GO2bank] [app upgrade] Set app force upgrade | https://pd.nextestate.com/browse/BUX-38827 | M111 | No | Critical | Medium | High | Medium | N/A | N/A | Medium | N/A | Yes | 2022-06-23
May 23,2023 | Megan Ackling | [QA Testing]ATM and AFT Limit Decrease for Regular Season - CoID 164 | https://pd.nextestate.com/browse/GBOS-62061 | M111 | No | High | N/A | N/A | N/A | N/A | Medium | N/A | N/A | No | 2022-06-23
2022-06-07 | Smitha Jonnala | [WMMC] OAuth redirect is not working as expected | https://pd.nextestate.com/browse/GB-80048 | M111 | Yes | N/A | N/A | Medium | N/A | N/A | N/A | N/A | Medium | Yes | 2022-06-23
2022-05-20 | Megan Ackling | Walgreens and CVS FeeSplit Setup for eCash Setup - GBOS | https://pd.nextestate.com/browse/FEAS-24667 | M111 | No | N/A | High | High | N/A | N/A | N/A | N/A | N/A | No | 2022-06-23
2022-06-06 | Sarath Krishnan | [GFT][MCsend]Create Adjusmentypes for Partner A2A and P2P | https://pd.nextestate.com/browse/GBOS-61750 | M111 | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No | 2022-06-23
2022-06-16 | Dennis Wiles | [GO2bank][Web] Add Domains to CSP Whitelisting | https://pd.nextestate.com/browse/BUX-38699 | M111 | No | N/A | N/A | High | High | N/A | N/A | N/A | N/A | No | 2022-06-23
2022-06-16 | Mark Sun | [QA ONLY] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BMAPP-22159 | M111 | No | N/A | Low | High | N/A |  | Low | Low | N/A | No | 2022-06-23
2022-06-16 | Mark Sun | [QA only] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BUX-38697 | M111 | No | N/A | Low | High | N/A |  | Low | Low | N/A | No | 2022-06-23
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Desktop browser) | https://pd.nextestate.com/browse/BUX-37261 | M111 | Yes | Critical | N/A | High | Low | N/A | Medium | Medium | N/A | Yes | 2022-06-23
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Mobile browser) | https://pd.nextestate.com/browse/BUX-37262 | M111 | Yes | Critical | N/A | High | Low | N/A | Medium | Medium | N/A | Yes | 2022-06-23
2022-05-20 | Tyler Penn | [iOS/Android][GO2bank] [ODP 2.0] Go-Live | https://pd.nextestate.com/browse/BMAPP-21834 | M111 | Yes | Critical | N/A | High | Low | N/A | Medium | Medium | N/A | Yes | 2022-06-23
2022-06-13 | Rita Webb | [COFO] Research Extensibility of Current Mobile 2FA Service | [GBOS-61873] [COFO][SPIKE] Research Extensibility of Current Mobile 2FA Service - GDCJira (nextestate.com) | M111 | No | N/A | Medium | High | N/A | N/A | Medium | Low | Low | No | 2022-06-23
2022-06-14 | Sarath Krishnan | [GFT]Update the Utility Core API to get Bin info to add Program code | https://pd.nextestate.com/browse/GBOS-62197 | M111 | No | N/A | High | High |  |  |  | High |  | No | 2022-06-23
2022-06-08 | Smitha Jonnala | BUX-37721: [Web] - [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BUX-37721 | M111 | No | N/A | Medium | Medium | N/A | N/A | N/A | N/A | Medium | No | 2022-06-23
2022-06-08 | Smitha Jonnala | BMAPP-21860: [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BMAPP-21860 | M111 | No | N/A | Medium | Medium | N/A | N/A | N/A | N/A | Medium | No | 2022-06-23
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25
2022-05-25

## Sheet2
Entry/Last Updated Date | Product Manager | Item | Jira Ticket | Milestone/Release Due Date | Requestor | Critical Defect | Regulatory/Compliance Urgency | Partner Priority | Product Value | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency | Defects | Is this a Hard Date
2022-05-20 | Tyler Penn | [Automate] GO2bank ODP Fee Reversal | https://pd.nextestate.com/browse/GBOS-61531 | M111 |  | Yes | Critical | N/A | Medium | N/A |  | Low | N/A | Medium | No
2022-05-20 | Tyler Penn | [iOS/Android][GO2bank] [ODP 2.0] Go-Live | https://pd.nextestate.com/browse/BMAPP-21834 | M111 |  | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Desktop browser) | https://pd.nextestate.com/browse/BUX-37261 | M111 |  | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Mobile browser) | https://pd.nextestate.com/browse/BUX-37262 | M111 |  | Yes | Critical | N/A | High | Low | $1.5M | Medium | Medium | N/A | Yes
2022-05-20 | Megan Ackling | Walgreens and CVS FeeSplit Setup for eCash Setup - GBOS | https://pd.nextestate.com/browse/FEAS-24667 | M111 |  | No | N/A | High | High | N/A | $227K Annual | N/A | N/A | N/A | No
May 23,2023 | Megan Ackling | [QA Testing]ATM and AFT Limit Decrease for Regular Season - CoID 164 | https://pd.nextestate.com/browse/GBOS-62061 | M111 |  | No | High | N/A | N/A | N/A | N/A | Medium | N/A | N/A | No
May 26,2022 | Tyler Penn | [BaaS][OD EligibilityProcessor] Enhancement to add retry mechanism when call DB to get data | https://pd.nextestate.com/browse/GBOS-62054 | M111 |  | Yes | High | N/A | High | Medium | N/A | Medium | Medium | High | Yes
2022-05-31 | Mark Sun | SCC payments: ACH payments reminder | https://pd.nextestate.com/browse/GBOS-62108 | M111 | Direct | Yes | Critical | N/A | High | N/A |  | N/A | N/A | N/A | No
2022-05-31 | Mark Sun | SCC payments: ACh return notifications | https://pd.nextestate.com/browse/GBOS-62135 | M111 | Direct | Yes | Critical | N/A | Medium | N/A |  | N/A | N/A | Medium | No
2022-06-02 | Mark Sun | [Customer Notification][GO2bank SCC] OFAC - Hard Decline | https://pd.nextestate.com/browse/GBOS-39848 | M111 |  | Yes | Critical | N/A | High | N/A |  | Critical | N/A | N/A | Yes
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey105] Tier Reinstated | https://pd.nextestate.com/browse/GBOS-62115 | M111 |  | Yes | High | N/A | High | N/A |  | Low | N/A | High | Yes
2022-06-03 | Mirko | Allow SMB BaaS partners to cancel pending ACH Pull transactions | https://pd.nextestate.com/browse/GBOS-62222 | M111 | BaaS | No | N/A | Low | Low | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Add logic for Check-Sum for Speedway - DB | https://pd.nextestate.com/browse/GSS-30854 | M111 |  | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Ziegler | Add logic for Check-Sum for Speedway - Code | https://pd.nextestate.com/browse/GSS-30687 | M111 |  | No | N/A | High | N/A | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Sarath Krishnan | [GFT][MCsend]Create Adjusmentypes for Partner A2A and P2P | https://pd.nextestate.com/browse/GBOS-61750 | M111 | GDN | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No
2022-06-06 | Sarath Krishnan | [GFT][Chime]Modify Link Card API Mandatory Fields based on Program code. | https://pd.nextestate.com/browse/GBOS-62236 | M111 | GDN | No | N/A | High | High | N/A |  | N/A | N/A | N/A | No
2022-06-07 | Smitha Jonnala | [WMMC] OAuth redirect is not working as expected | https://pd.nextestate.com/browse/GB-80048 | M111 |  | Yes | N/A | N/A | Medium | N/A | N/A | N/A | N/A | Medium | Yes
2022-06-08 | Smitha Jonnala | BUX-37721: [Web] - [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BUX-37721 | M111 |  | No | N/A | Medium | Medium | N/A | N/A | N/A | N/A | Medium | No
2022-06-08 | Smitha Jonnala | BMAPP-21860: [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BMAPP-21860 | M111 |  | No | N/A | Medium | Medium | N/A | N/A | N/A | N/A | Medium | No
2022-06-13 | Rita Webb | [COFO] Research Extensibility of Current Mobile 2FA Service | [GBOS-61873] [COFO][SPIKE] Research Extensibility of Current Mobile 2FA Service - GDCJira (nextestate.com) | M111 | Risk | No | N/A | Medium | High | N/A | N/A | Medium | Low | Low | No
2022-06-13 | Rita Webb | [COFO] Ethoca - Data Types Not passing correctly | [COFO-49401] [RSK] [Disputes] [SPIKE] Determine why certain Data Types are not passing accurately to Ethoca - GDCJira (nextestate.com) | M111 | Risk | No | Medium | Low | Medium | N/A | N/A | Medium | Low | N/A | No
2022-06-14 | Sarath Krishnan | [GFT]Update the Utility Core API to get Bin info to add Program code | https://pd.nextestate.com/browse/GBOS-62197 | M111 | GDN | No | N/A | High | High |  |  |  | High |  | No
2022-06-14 | Mark Sun | [QA][Go-Live] Refund ATM Fees over 25% of credit limit in first year | https://pd.nextestate.com/browse/GBOS-62337 | M111 | Direct | Yes | Critical | High | High | N/A |  | Medium | N/A | High | Yes
2022-06-15 | Mark Sun | [SCC] Block non-SSN DDA applying for an SCC | https://pd.nextestate.com/browse/GBOS-62345 | M111 | Direct | No | Critical | Low | Medium | N/A |  | High | High | High | No
2022-06-16 | Mark Sun | [SCC] Expected Master file wasn't processed automatically | https://pd.nextestate.com/browse/GBOS-62281 | M111 | Direct | Yes | Critical | Low | Medium | N/A |  | High | High | High | No
2022-06-16 | Mark Sun | [SCC] 6/5 statement file initial processing error | https://pd.nextestate.com/browse/GBOS-62275 | M111 | Direct | Yes | Critical | Low | Medium | N/A |  | High | High | High | No
2022-06-16 | Mark Sun | [SCCBatchProcessorJob_Delinquincy] Add ability to reprocess accounts | https://pd.nextestate.com/browse/GBOS-62234 | M111 | Direct | Yes | Critical | Low | Medium | N/A |  | High | High | High | No
2022-06-16 | Mark Sun | SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/GBOS-59037 | M111 | Direct | No | N/A | Low | High | N/A |  | Low | Low | N/A | No
2022-06-16 | Mark Sun | [QA ONLY] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BMAPP-22159 | M111 | Direct | No | N/A | Low | High | N/A |  | Low | Low | N/A | No
2022-06-16 | Mark Sun | [QA only] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BUX-38697 | M111 | Direct | No | N/A | Low | High | N/A |  | Low | Low | N/A | No
2022-06-16 | Dennis Wiles | [GO2bank][Web] Add Domains to CSP Whitelisting | https://pd.nextestate.com/browse/BUX-38699 | M111 | Direct | No | N/A | N/A | High | High | N/A | N/A | N/A | N/A | No
2022-06-22 | Tyler Penn | [Gateway] [GO2bank] [app upgrade] Set app force upgrade | https://pd.nextestate.com/browse/BUX-38827 | M111 | Direct | No | Critical | Medium | High | Medium | $1.5M | N/A | Medium | N/A | Yes

## Sheet3
DATA
Due Date
M107
2022-05-19
R133
2022-05-31
M108
2022-06-02
M109
2022-06-16
M110
2022-06-30
R134
2022-07-05
M111
2022-07-14
M112
2022-07-28
R135
2022-08-09
M113
2022-08-11
M114
2022-08-25
M115
2022-09-08
R136
2022-09-13
M116
2022-09-22
M117
2022-10-06
M118
2022-10-20
R137
2022-10-25
M119
2022-11-03
M120
2022-11-17
R138
2022-11-29
M121
2022-12-01
M122
2022-12-15
R139
2023-01-03
M123
2023-01-05