## Sheet
Entry/Last Updated Date | Product Manager | Item | Jira Ticket | Milestone/Release Due Date | Critical Defect | Regulatory/Compliance Urgency | Partner Priority | Product Value | Marketing Urgency | Revenue | InfoSec/Fraud/Risk Urgency | Engineering Urgency | Defects | Is this a Hard Date | Last Date of Prioritzation | Deferred | Override
2022-06-14 | Mark Sun | [QA][Go-Live] Refund ATM Fees over 25% of credit limit in first year | https://pd.nextestate.com/browse/GBOS-62337 | M111 | True | Critical | High | High | N/A | N/A | Middle | N/A | High | True | 2022-06-23 | False | False
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Desktop browser) | https://pd.nextestate.com/browse/BUX-37261 | M111 | True | Critical | N/A | High | Low | N/A | Middle | Middle | N/A | True | 2022-06-23 | False | False
2022-05-20 | Tyler Penn | [Web] [GO2bank] [ODP 2.0] Go-Live (Mobile browser) | https://pd.nextestate.com/browse/BUX-37262 | M111 | True | Critical | N/A | High | Low | N/A | Middle | Middle | N/A | True | 2022-06-23 | False | False
2022-05-20 | Tyler Penn | [iOS/Android][GO2bank] [ODP 2.0] Go-Live | https://pd.nextestate.com/browse/BMAPP-21834 | M111 | True | Critical | N/A | High | Low | N/A | Middle | Middle | N/A | True | 2022-06-23 | False | False
2022-05-20 | Tyler Penn | [Automate] GO2bank ODP Fee Reversal | https://pd.nextestate.com/browse/GBOS-61531 | M111 | True | Critical | N/A | Middle | N/A | N/A | Low | N/A | Middle | False | 2022-06-23 | False | False
2022-06-02 | Tyler Penn | ODP 2.0 : [TRIGGER FOR NTKey105] Tier Reinstated | https://pd.nextestate.com/browse/GBOS-62115 | M111 | True | High | N/A | High | N/A | N/A | Low | N/A | High | True | 2022-06-23 | False | False
2022-06-07 | Smitha Jonnala | [WMMC] OAuth redirect is not working as expected | https://pd.nextestate.com/browse/GB-80048 | M111 | True | N/A | N/A | Middle | N/A | N/A | N/A | N/A | Middle | True | 2022-06-23 | False | False
2022-06-22 | Tyler Penn | [Gateway] [GO2bank] [app upgrade] Set app force upgrade | https://pd.nextestate.com/browse/BUX-38827 | M111 | False | Critical | Middle | High | Middle | N/A | N/A | Middle | N/A | True | 2022-06-23 | False | False
2022-06-15 | Mark Sun | [SCC] Block non-SSN DDA applying for an SCC | https://pd.nextestate.com/browse/GBOS-62345 | M111 | False | Critical | Low | Middle | N/A | N/A | High | High | High | False | 2022-06-23 | False | False
2022-05-23 | Megan Ackling | [QA Testing]ATM and AFT Limit Decrease for Regular Season - CoID 164 | https://pd.nextestate.com/browse/GBOS-62061 | M111 | False | High | N/A | N/A | N/A | N/A | Middle | N/A | N/A | False | 2022-06-23 | False | False
2022-06-14 | Sarath Krishnan | [GFT]Update the Utility Core API to get Bin info to add Program code | https://pd.nextestate.com/browse/GBOS-62197 | M111 | False | N/A | High | High | N/A | N/A | N/A | High | N/A | False | 2022-06-23 | False | False
2022-05-20 | Megan Ackling | Walgreens and CVS FeeSplit Setup for eCash Setup - GBOS | https://pd.nextestate.com/browse/FEAS-24667 | M111 | False | N/A | High | High | N/A | N/A | N/A | N/A | N/A | False | 2022-06-23 | False | False
2022-06-06 | Sarath Krishnan | [GFT][MCsend]Create Adjusmentypes for Partner A2A and P2P | https://pd.nextestate.com/browse/GBOS-61750 | M111 | False | N/A | High | High | N/A | N/A | N/A | N/A | N/A | False | 2022-06-23 | False | False
2022-06-13 | Rita Webb | [COFO] Research Extensibility of Current Mobile 2FA Service | [GBOS-61873] [COFO][SPIKE] Research Extensibility of Current Mobile 2FA Service - GDCJira (nextestate.com) | M111 | False | N/A | Middle | High | N/A | N/A | Middle | Low | Low | False | 2022-06-23 | False | False
2022-06-08 | Smitha Jonnala | BUX-37721: [Web] - [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BUX-37721 | M111 | False | N/A | Middle | Middle | N/A | N/A | N/A | N/A | Middle | False | 2022-06-23 | False | False
2022-06-08 | Smitha Jonnala | BMAPP-21860: [Server] [Go2bank and Chirp] Transactions API is not returning masked external account values for SCC transactions | https://pd.nextestate.com/browse/BMAPP-21860 | M111 | False | N/A | Middle | Middle | N/A | N/A | N/A | N/A | Middle | False | 2022-06-23 | False | False
2022-06-16 | Mark Sun | [QA ONLY] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BMAPP-22159 | M111 | False | N/A | Low | High | N/A | N/A | Low | Low | N/A | False | 2022-06-23 | False | False
2022-06-16 | Mark Sun | [QA only] SCC declines can re-apply after 30 days | https://pd.nextestate.com/browse/BUX-38697 | M111 | False | N/A | Low | High | N/A | N/A | Low | Low | N/A | False | 2022-06-23 | False | False
2022-06-16 | Dennis Wiles | [GO2bank][Web] Add Domains to CSP Whitelisting | https://pd.nextestate.com/browse/BUX-38699 | M111 | False | N/A | N/A | High | High | N/A | N/A | N/A | N/A | False | 2022-06-23 | False | False